## Index & Instructions
Architecting Intelligence — AI Governance & Qualification Framework
Enterprise-grade governance toolkit for AI use case qualification, pre-deployment governance, model change management, and portfolio capacity planning.
WORKBOOK CONTENTS
# | Sheet Name | Purpose | When to Use | Owner | Review Frequency
1 | AI Qualification Checklist | 8-question gate to determine if AI is the right tool. Forces formula/RPA evaluation before AI is approved. | Before any AI implementation is proposed to the Review Board | Enterprise Architect | Per project request
2 | AI Governance Checklist | 32 pre-deployment governance controls across 7 categories. Blocker/Required/Recommended classification. | After qualification approved. Before architecture build commences. | AI CoE Lead + Risk Owner | Per deployment
3 | Model Change Management | Change classification (Class 1–4), test scope, tier definitions, and timeline gates for every model version change. | Every time a model version change is proposed or notified by vendor. | Risk Owner + QA Lead | Per model change
4 | Portfolio Capacity Register | Live register of all AI deployments with bandwidth scoring. Tracks utilisation vs red line (70%). | Reviewed weekly by AI CoE. Checked before any new deployment is approved. | AI CoE Lead | Weekly
5 | Review Board Decision Log | Permanent audit trail of all AI implementation requests and board decisions. | Updated after every Review Board session. 7-year retention minimum. | Board Chair / AI CoE | Per board decision
CORE GOVERNANCE PRINCIPLES
P1 | Implement AI when required — not because it is easy. | The default answer to any AI implementation request is no. The project team proves AI is necessary — not the governance team proving it isn't.
P2 | Formula first. RPA second. AI third. | If a deterministic formula or rule set solves the problem for 95%+ of cases, AI is not required. Governance overhead of AI must be justified by genuine capability need.
P3 | Every test case is permanent. | The test library is append-only. Edge cases and low-frequency scenarios are never removed. A passing test case is proof the control works — not a candidate for deletion.
P4 | Go-live governance is not production governance. | An agent that passed UAT is an agent that passed UAT. Production governance requires continuous monitoring, model change management, and quarterly review — indefinitely.
P5 | The vendor's 'minor' is your governance risk. | Any model version change regardless of vendor classification triggers full re-validation. You cannot verify what changed internally. Your test library is the only ground truth you control.
P6 | Bandwidth is a shared constraint, not a project resource. | Governance team capacity for model changes, monitoring, and incident response is finite and managed at portfolio level. No project owns governance capacity — the portfolio does.

## AI Qualification Checklist
AI Use Case Qualification Checklist — Enterprise Review Board
Complete this checklist before any AI implementation is approved. Default board position: NOT APPROVED. Project team must prove AI is required.
# | Gate Question | Category | Answer (Yes/No/N/A) | If YES | If NO | Evidence Required | Finding (Blocker/Required/Rec) | Reviewer Notes
Q1 | Can the output be produced by a deterministic formula or rule set for the majority of cases? | Use Case Fit |  | Implement formula/rule engine. Do NOT scope AI. Handle exceptions with human review. | Proceed to Q2. | Formula evaluation document signed by SME | Blocker
Q2 | Is the input data structured and the process steps fully mappable end-to-end? | Use Case Fit |  | Implement RPA or workflow automation. AI adds governance cost with no capability advantage. | Proceed to Q3. | Process map / data structure assessment | Blocker
Q3 | Does the problem genuinely require cognitive interpretation — unstructured data, variable context, multi-factor judgement? | Use Case Fit |  | AI may be appropriate. Continue qualification. | Return to Q1 or Q2. Problem has been miscategorised. | Use case description with examples of ambiguous inputs | Blocker
Q4 | Has a non-AI alternative been formally evaluated and documented as insufficient? | Alternatives |  | Document why alternative was rejected. This is the audit trail. | Return to Q1. Evaluation not completed. AI not approved on convenience. | Alternatives evaluation report with sign-off | Blocker
Q5 | Is the organisation's current AI governance maturity sufficient to manage this deployment safely? | Governance Readiness |  | Document evidence. Governance team confirms bandwidth available. | Queue. Do not deploy until maturity gap is closed. | Governance maturity assessment, bandwidth score | Blocker
Q6 | Is this a high-risk domain (regulated decisions, financial transactions, patient impact, legal exposure)? | Risk Classification |  | AI maturity requirement doubles. Require demonstrated production performance from comparable deployment. | Standard qualification continues. | Risk classification signed by risk function (not project team) | Blocker
Q7 | Can the AI decision be explained to a regulator, auditor, or affected individual in plain language? | Explainability |  | Document the explainability mechanism. Must exist at deployment — not promised for later. | Blocked. Non-explainable AI in regulated context is non-compliant before go-live. | Explainability design document | Blocker
Q8 | Does portfolio bandwidth capacity exist to govern, monitor, and respond to model changes? | Portfolio Capacity |  | Governance team confirms in writing. Bandwidth score added to register. | Queue. Portfolio at capacity. Not a negotiation. | Portfolio bandwidth score, governance team allocation confirmation | Blocker
Q9 | Is the agent's scope limited to genuinely cognitive tasks only (no formula-calculable sub-tasks included)? | Scope Control |  | Document scope boundaries. Rule-based pre-filters defined. | Reduce agent scope. Remove deterministic sub-tasks from AI scope. | Agent scope definition document with pre-filter specification | Required
Q10 | Has the vendor's historical model release cadence been documented as a project input? | Vendor Risk |  | Release cadence factored into governance cost and bandwidth scoring. | Vendor assessment incomplete. Do not proceed to architecture approval. | Vendor release history, upgrade notification SLA in contract | Required
Q11 | Is the foundation model version pinnable and independently rollback-capable within 30 minutes? | Model Sovereignty |  | Version pinning confirmed at API gateway level. Rollback tested. | Blocked. Model sovereignty is non-negotiable for production deployment. | Version pin configuration, rollback test record | Blocker
Q12 | Has the full governance cost been included in the business case (test library, monitoring, change cycles)? | Business Case |  | Business case approved with full TCO including governance overhead. | Business case incomplete. Return to project sponsor. | Business case document with governance cost line items | Required
OVERALL QUALIFICATION RESULT | [6 empty] | APPROVED — Proceed to governance checklist

## AI Governance Checklist
AI Governance Checklist — Pre-Deployment & Production Controls
All Blocker findings must be resolved before deployment. Required findings must be remediated within 30 days. Recommended findings logged in AI System Register.
# | Control | Category | Classification | Status (Pass/Fail/Pending) | Evidence Required | Evidence Location / Reference | Owner | Review Date | Notes
MODEL SOVEREIGNTY
G-01 | Foundation model version is pinned to a specific named version — no floating alias ('latest') | Model Sovereignty | Blocker |  | Version pin confirmed at API gateway level, not documentation only
G-02 | Vendor provides contractual minimum 30-day advance notice of model version deprecation or forced upgrade | Model Sovereignty | Blocker |  | Executed contract clause — reviewed by legal, not filed
G-03 | Rollback to previous model version achievable within 30 minutes without a deployment cycle — tested | Model Sovereignty | Blocker |  | Rollback test record with timestamp and approver
G-04 | For Tier 1 agents: open-weights model on controlled infrastructure evaluated and decision documented | Model Sovereignty | Required |  | Architecture decision record with rationale
CHANGE MANAGEMENT
G-05 | Any model version change classified as Class 1–4 before validation scope is determined | Change Management | Blocker |  | Change classification procedure and sign-off authority matrix
G-06 | Full regression test library exists — covers 100% of transaction/domain types including edge cases | Change Management | Blocker |  | Test library register with domain coverage % report
G-07 | Class 1 and Class 2 changes require 100% full library re-validation — no sample testing permitted | Change Management | Blocker |  | Validation policy document signed by risk owner
G-08 | 72-hour parallel shadow run completed before any model version enters production | Change Management | Required |  | Parallel run report with discrepancy analysis
G-09 | Model version change requires risk owner sign-off — not technology team alone | Change Management | Required |  | Sign-off record in AI system register with date
G-10 | 90-day stabilisation period enforced — no model upgrade within 90 days of initial go-live | Change Management | Required |  | Stabilisation period logged in deployment timeline
MONITORING
G-11 | Canary monitoring active — known transactions with predefined outputs run every 2–4 hours in production | Monitoring | Blocker |  | Canary suite configuration, alert threshold definition, test log sample
G-12 | Decision distribution baseline captured at go-live — drift threshold defined per domain (≤3% before alert) | Monitoring | Required |  | Baseline distribution report, threshold configuration
G-13 | Exception rate trending monitored — unusual spike in any domain triggers review within 4 hours | Monitoring | Required |  | Monitoring dashboard configuration, alert runbook
G-14 | Monthly outcome reconciliation — agent decisions compared against downstream business outcomes | Monitoring | Recommended |  | Reconciliation procedure and sample report
BLAST RADIUS
G-15 | Hard transaction caps enforced in integration layer code — not in model prompt. Reviewed directly. | Blast Radius | Blocker |  | Integration layer code review, threshold breach test record
G-16 | Automatic suspension threshold defined — agent halts and escalates if decision pattern deviates beyond threshold | Blast Radius | Blocker |  | Suspension logic code review, threshold test evidence
G-17 | Kill switch documented, tested, and executable in under 5 minutes without deployment cycle | Blast Radius | Blocker |  | Kill switch procedure, test record, authorised activator list
G-18 | Segregation of duties enforced — agent initiating action cannot be same agent approving it | Blast Radius | Required |  | Architecture diagram showing segregation, code review
DATA SECURITY
G-19 | Zero-training clause in vendor contract — covers sub-processors, embeddings, and metadata explicitly | Data Security | Blocker |  | Executed MSA with clause highlighted, legal review sign-off
G-20 | All data processing geographically restricted to approved jurisdictions — including failover paths | Data Security | Blocker |  | Cloud region config, failover endpoint mapping, legal sign-off
G-21 | RBAC enforced at system access, retrieval scope, and output scope — verified by functional testing | Data Security | Blocker |  | RBAC matrix, least privilege test evidence
G-22 | PII sanitisation validated against actual production data types — false negative rate measured | Data Security | Required |  | Masking logic documentation, production data test results
ACCOUNTABILITY
G-23 | Single named risk owner assigned — not a team. Accountable for agent behaviour in production. | Accountability | Blocker |  | Named individual in AI system register with formal acceptance
G-24 | AI system register entry complete — model version, risk classification, validation date, open findings | Accountability | Required |  | AI system register record with all 9 required fields populated
G-25 | AI-specific incident response procedure documented and exercised in tabletop scenario | Accountability | Required |  | Incident response procedure, tabletop exercise record
G-26 | Quarterly governance review scheduled — risk owner and AI CoE. Not optional for Tier 1 agents. | Accountability | Recommended |  | Quarterly review calendar entry, previous review record
SCOPE CONTROL
G-27 | Agent scope limited to cognitive tasks only — all deterministic sub-tasks removed to rule engine / formula | Scope Control | Blocker |  | Agent scope definition document, pre-filter specification
G-28 | AI qualification checklist completed and approved before architecture build commenced | Scope Control | Blocker |  | Signed qualification checklist with Review Board sign-off
G-29 | Governance cost included in approved business case — test library, monitoring, change cycles, rollback | Scope Control | Required |  | Business case document with governance cost line items approved
PORTFOLIO CAPACITY
G-30 | Portfolio bandwidth score calculated and current utilisation below 70% red line | Portfolio Capacity | Blocker |  | Portfolio dashboard screenshot at time of approval
G-31 | Go-live date staggered minimum 30 days from any other Tier 1 agent go-live | Portfolio Capacity | Required |  | Portfolio deployment calendar showing stagger
G-32 | 20% governance bandwidth buffer maintained — not allocated to this or any other project | Portfolio Capacity | Required |  | Bandwidth allocation confirmation from AI CoE lead
OVERALL GOVERNANCE STATUS | [7 empty] | APPROVED FOR DEPLOYMENT

## Model Change Management
Model Change Management Grid — Classification, Timeline & Test Validation
Every model version change must be classified before validation scope is determined. Zero regression failures permitted. Test library is append-only — no cases are ever deleted.
Change Class | Description | Example Triggers | Test Scope Required | Tier A (Critical Path) | Tier B (Domain Coverage) | Tier C (Edge Cases) | Tier D (Regression) | Parallel Run | Min Timeline (Bus. Days) | Risk Owner Sign-off | Notes
Class 1 Major | Foundation model replaced — new model family or provider switch | GPT-4 → GPT-5 Claude 3 → Claude 4 Any provider switch | 100% Full Library | ✓ Mandatory | ✓ Mandatory | ✓ Mandatory | ✓ Mandatory | 72 hrs | 15 | CRO + Risk Owner
Class 2 Minor | Version increment on same foundation model | gpt-4o → gpt-4o-2025-11 Claude 3.5 → Claude 3.6 Any patch version bump | 100% Full Library | ✓ Mandatory | ✓ Mandatory | ✓ Mandatory | ✓ Mandatory | 72 hrs | 7 | Risk Owner
Class 3 Patch | Configuration or parameter change on same model version | Temperature change System prompt update Context window change top-p / top-k change | Affected domains + full regression | ✓ Mandatory | Affected domains only | ✓ Mandatory | ✓ Mandatory | 24 hrs | 3 | Risk Owner
Class 4 Hotfix | Emergency rollback to previous pinned version due to live incident | Production incident requires immediate reversion to v(n-1) | Canary suite + critical path | ✓ Mandatory | ✗ Not required | ✗ Not required | Tier D only | 4 hrs | 0.5 | Risk Owner (post-facto CRO)
TEST LIBRARY — TIER DEFINITIONS AND MINIMUM REQUIREMENTS
Tier | Name | Description | Min Cases Per Domain | Run Frequency | Never Removed? | Who Creates | Failure Tolerance | Scope (Change Class) | Automated? | Notes
Tier A | Critical Path | 20% of transactions representing 80% of business risk or volume | 10 | Every test cycle (all change classes) | Yes | QA lead + domain SME | Zero | All classes | Yes — results in 30 min
Tier B | Domain Coverage | Every distinct transaction category mapped to business domain taxonomy. Every category covered regardless of frequency. | 5 minimum | Class 1, 2, 3 | Yes | Domain SME + QA | Zero for Blockers | Class 1, 2, 3 | Yes
Tier C | Edge Cases & Boundaries | Previously failed transactions, decision boundary cases, rare but legitimate combinations, multi-procedure claims, unusual inputs. | 3 minimum | Class 1, 2, 3 | Yes — NEVER deleted | Incident response pipeline (auto-added within 5 days) | Zero | Class 1, 2, 3 | Yes
Tier D | Adversarial & Regression | Every historical production incident. Every bug fixed in production. Attempts to manipulate via unusual input formatting. | 1 per incident | Class 1, 2 + hotfix | Yes — append only | Post-incident process (mandatory within 5 days) | Zero — single regression failure blocks upgrade | Class 1, 2, Hotfix | Yes

## Portfolio Capacity Register
AI Portfolio Capacity Register — Bandwidth Utilisation & Deployment Queue
Red line: 70% total utilisation. Optimal ceiling: 50%. 20% buffer must remain unallocated at all times. No new deployments approved above red line without CEO sign-off.
BANDWIDTH SCORING GUIDE: Score each component 1–5. Sum = project bandwidth weight. Total portfolio utilisation = SUM(all weights) ÷ max capacity × 100%
Project / Agent Name | Business Domain | Foundation Model (Pinned) | Agent Tier | Transaction Volume Score (1–5) | Model Change Frequency Score (1–5) | Regulatory Exposure Score (1–5) | Agent Autonomy Score (1–5) | Test Library Size Score (1–5) | Total Bandwidth Weight | Lifecycle Stage | Go-Live Date | Next Change Window | Risk Owner
Dental Claims Agent | Insurance — BFSI | claude-3-5-sonnet-20241022 | 1 | 4 | 3 | 5 | 4 | 3 | 17 | Active — monitoring | 2024-06-01 | 2025-03-15 | J. Smith
Prior Auth Agent | Healthcare — BFSI | gpt-4o-2024-08-06 | 1 | 3 | 4 | 5 | 3 | 2 | 12 | Stabilisation | 2024-09-15 | 2025-04-01 | M. Patel
Provider Credentialing | Healthcare — BFSI | claude-3-5-haiku-20241022 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | Planning | TBC | TBC | R. Lee
PORTFOLIO SUMMARY METRICS
Total active agents | 2
Total bandwidth consumed | 29
Max governance capacity (set manually) | 25
Current utilisation % | 116%
Status vs red line (70%) | RED — Above limit
Deployments in planning queue | 1

## Review Board Decision Log
AI Review Board — Decision Log & Approval Register
Permanent audit trail of all AI implementation requests reviewed by the board. Every decision is logged regardless of outcome. Records retained for 7 years minimum.
Request Ref | Project Name | Business Domain | Requested Implementation | Date Submitted | Qualification Checklist Ref | Board Decision | Decision Rationale | Conditions / Remediation Required | Review Board Chair | Decision Date | Re-review Date (if req.) | Notes
AIR-001 | Dental Claims Processing | Insurance — BFSI | Agentic AI — end-to-end claim processing | 2024-03-01 | QC-001 | Approved with Conditions | Cognitive interpretation of multi-diagnosis claims justified. Agent scope must exclude deterministic frequency limit checks (redirect to rule engine). | 1. Remove D0274 frequency check to rule pre-filter. 2. Full test library built before go-live. 3. 90-day stabilisation enforced. | R. Ramadasan | 2024-03-11 | 2024-09-01
AIR-002 | Premium Calculation Engine | Insurance — BFSI | AI model for premium calculation | 2024-05-10 | QC-002 | Redirected to Formula/RPA | Premium calculation is deterministic — base rate × risk factor × age bracket. Formula produces correct result for 100% of cases. AI adds governance cost with zero capability benefit. | Implement actuarial formula engine. Re-submit if genuinely ambiguous cases identified with evidence. | R. Ramadasan | 2024-05-20 |  | Classic formula-not-AI case
AIR-003 | Provider Credentialing Agent | Healthcare — BFSI | Agentic AI — credential verification | 2024-07-15 | QC-003 | Queued — Capacity | Use case qualifies for AI. Portfolio at 68% utilisation — above optimal ceiling. Dental claims agent in stabilisation period. Queue until Q4 capacity review. | Revisit at Q4 portfolio review. Governance team confirms capacity before architecture approval. | R. Ramadasan | 2024-07-25 | 2024-10-01